## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2228-swen-261-01-2-BobbyFanGroup
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Buyer I want to be able to add or remove products to my shopping cart so that I can purchase products of my choosing together. | Given A SHOPPING CART when I ADD ITEMS then I EXPECT ITEMS TO BE IN THE CART. | Pass | DF; 7/18/2023
| Given A SHOPPING CART when I REMOVE ITEMS then I EXPECT ITEMS TO BE REMOVED FROM THE CART. | Pass | DF; 7/18/2023
As an Owner I want to update inventory so customers can stay updated on as well as purchase in-stock products. | Given that I am the owner when I access the inventory then I expect to be able to add items. | Pass | RS; 7/18/2023
| Given that I am the owner when I access the inventory then I expect to be able to remove items. | Pass | RS; 7/18/2023
| Given that I am the owner when I access the inventory then I expect to be able to change the stock of each item. | Pass | RS; 7/18/2023
As an Owner I want to be able to login with my username so that I can access administrative privileges to update the inventory. | Given that I am the owner when I login using my details then I expect to be able to access my administrator permissions. | Pass | DF; 7/18/2023
| Given that I am not the owner when I login using my details then I expect to not be able to edit items or any admin tasks. | Pass | CK; 7/17/2023
As a Buyer I want to be able to login with my username so that I can access my saved shopping cart from the last session. | Given I am a buyer when I want to access the estore then I can log into the website with my username. | Pass | RS; 7/18/2023
| Given I am a buyer who was already created an account when I log in then I want to be able to access my already-made account. | Pass | SP; 7/18/2023
As a Buyer I want to be able to view my past orders so that I can see what I’ve already ordered, and to confirm that I’ve ordered something. | Given that I have purchased items in the past when I access my previous orders via the user menu then I expect to see each order. | Pass | RS; 7/18/2023